# ESEA FLEXIBILITY PART A MONITORING REPORT FOR THE WASHINGTON OFFICE OF SUPERINTENDENT OF PUBLIC INSTRUCTION

## Overview Of ESEA Flexibility Monitoring

The U.S. Department of Education (ED) is committed to supporting State educational agencies (SEAs) as they implement ambitious reform agendas through their approved ESEA flexibility requests.  Consistent with this commitment, ED has developed a monitoring process that is designed to both ensure that each SEA implements its plan fully, effectively, and in a manner that is consistent with its approved request and the requirements of ESEA flexibility, as well as support each SEA with technical assistance to help ensure its implementation increases the quality of instruction and improves student achievement for all students in the State and its local educational agencies (LEAs).  Through this process, ED aims to productively interact with SEAs and shift from a focus primarily on compliance to one focused on outcomes.

For the 2012–2013 school year, ED has divided its ESEA flexibility monitoring process into three components, which are designed to align with the real-time implementation occurring at the SEA, LEA, and school levels and be differentiated based on an SEA’s progress and depth of work:

- Part A provided ED with a deeper understanding of each SEA’s goals and approaches to implementing ESEA flexibility and ensured that each SEA had the critical elements of ESEA flexibility in place to begin implementation of its plan in the 2012–2013 school year.  Part A was conducted through desk monitoring.

- Parts B and C, which are under development, will include a broader look at an SEA’s implementation of ESEA flexibility across all three principles, including its transition to college- and career-ready standards, its process for developing and implementing teacher and principal evaluation and support systems, and follow-up monitoring on the implementation of interventions in priority and focus schools.  Parts B and C reviews also will include a closer examination of the use of annual measureable objectives (AMOs), graduation rate targets, and other measures to drive supports and incentives in other Title I schools.  In addition, Parts B and C monitoring will address select unwaived Title I requirements and any “next steps” identified in the ESEA Flexibility Part A Monitoring Report.  These reviews will be conducted through a combination of on-site monitoring, desk monitoring, and progress checks that will be differentiated based on an individual SEA’s circumstances and request.  The format of future reports may vary from Part A.

ED will support each SEA in its implementation of ESEA flexibility across all three monitoring components and will work with each SEA to identify areas for additional technical assistance.

This ESEA Flexibility Part A Monitoring Report provides feedback to the Washington Office of Superintendent of Public Instruction (OSPI) on its progress in implementing the components of ESEA flexibility identified in the document titled ESEA Flexibility Part A Monitoring Protocol to ensure the SEA implements ESEA flexibility fully, effectively, and in a manner that is consistent with the SEA’s approved request and the requirements of ESEA flexibility.  This report is based on information provided through SEA-submitted documentation, a monitoring call conducted with OSPI staff on September 25, 2012, and a follow-up exit conference phone call held on October 5, 2012.  Generally, this report does not reflect steps taken by the SEA after the exit conference.

The report consists of the following sections:

- Highlights of OSPI’s Implementation of ESEA Flexibility.  This section identifies key accomplishments in the SEA’s implementation of ESEA flexibility as of the SEA’s monitoring call on September 25, 2012.

- Summary of OSPI’s Implementation of ESEA Flexibility and Next Steps.  This section provides a snapshot of the SEA’s progress in implementing each component of ESEA flexibility or unwaived Title I requirement based on the evidence OSPI described during its monitoring phone call on September 25, 2012, through written documentation provided to ED, and any further clarifications provided by the SEA during its exit conference phone call on October 5, 2012.  Where appropriate, this section also includes a set of “next steps” that were discussed with the SEA during its exit conference phone call, to ensure that the SEA implements the components of ESEA flexibility consistent with the principles and timelines in ESEA Flexibility and the OSPI’s approved request.

## Highlights Of OSPI’s Implementation Of Esea Flexibility

- Based on the information provided during the monitoring conference phone call and through written documentation, OSPI’s work implementing ESEA flexibility includes the following key accomplishments:

  - Ongoing communication with superintendents and principals regarding identification of reward, priority, focus, and emerging schools and expectations regarding implementation of interventions in these schools during the transition to the new index.

  - Use of State-level liaisons to support and monitor work in each priority and focus school.  As of early October 2012, each school had received at least one onsite visit.

## Summary Of OSPI’s Progress Implementing ESEA Flexibility And Next Steps

### Principle 2: State-Developed Differentiated Recognition, Accountability, and Support

| Component 2.A | Develop and implement beginning in the 2012–2013 school year a system of differentiated recognition, accountability, and support for all LEAs in the State and for all Title I schools in these LEAs. |
| --- | --- |
| Summary of Progress | OSPI indicated during the monitoring call that while it used its transitional system to identify schools this year, it had not yet used its new index to identify schools under its system of differentiated recognition, accountability, and support based on 2011–2012 data. ED conditioned approval of OSPI’s ESEA flexibility request based on the fact that OSPI would use the 2012–2013 school year to study and refine its index and could fully meet Principle 2 for the 2012–2013 school year while it continues to finalize its index. |
| Next Steps | ED will follow up with OSPI in Part B monitoring to ensure that OSPI is on track to meet this condition. |

| Assurance 7 | Report to the public its lists of reward schools, priority schools, and focus schools at the time the SEA is approved to implement flexibility, and annually thereafter, it will publicly recognize its reward schools as well as make public its lists of priority and focus schools if it chooses to update those lists. |
| --- | --- |
| Summary of Progress | OSPI publicly reported its lists of 58 reward schools, 46 priority schools, and 92 focus schools on July 10, 2012 by posting the lists on the SEA’s website at: http://www.k12.wa.us/ESEA/PublicNotice.aspx (valid as of December 18, 2012). OSPI notified each superintendent with one or more schools on the lists prior to making the lists public. |
| Next Steps | None. |

| Component 2.D | Effect dramatic, systemic change in the lowest-performing schools by publicly identifying priority schools and ensuring that each LEA with one or more of these schools implements, for three years, meaningful interventions aligned with the turnaround principles in each of these schools beginning no later than the 2014–2015 school year. |
| --- | --- |
| Summary of Progress | For the 2012–2013 school year, OSPI indicated that all 46 of its priority schools will implement interventions. Twenty-seven of these priority schools are schools receiving School Improvement Grant (SIG) funds to implement one of four SIG models and the remaining 19 priority schools are implementing other interventions aligned with all of the turnaround principles. OSPI noted that SIG schools are already implementing one of the four SIG models. OSPI explained that non-SIG priority schools had developed and submitted action plans to guide their implementation of interventions. At the time of the monitoring call, OSPI was reviewing these action plans using peer reviewers from across the State to assist with the review. OSPI expected non-SIG priority schools to start implementation by November 1, 2012. OSPI indicated that it would identify a second cohort of priority schools during the winter of the 2012–2013 school year, and those schools will begin implementation in the 2013–2014 school year. OSPI also noted that it was still considering how additional priority schools will be identified as the index is refined, but expressed a commitment to using data-driven decision making and addressing the needs of the lowest-performing schools. During the monitoring call, OSPI explained that it would coordinate support to priority schools based on the results of needs assessments and will use differentiated coaching based on the specific technical assistance needs in schools whose implementation is deemed to be “off track.” OSPI noted that it was shifting to an online planning tool to track schools’ progress on their action plans. During the monitoring call, OSPI noted that a majority of schools in the State use a voluntary self-assessment tool to evaluate the quality of teachers and principals, as well as to drive targeted professional development on instructional practices. OSPI added that additional funding and at least 30 days of coaching will be provided for each priority school to support implementation of its plan. OSPI explained that all non-SIG priority schools would receive external needs assessments in September and October, 2012. Findings and recommendations would be used to develop their Student and School Success Action Plan. OSPI indicated that both the needs assessment and the final Student and Success Action Plan would be anchored in the turnaround principles. OSPI noted that these turnaround principles are referred to as “Student and School Success Principles,” and the online action planning tool is organized around key research-based educator practices aligned with each principle. OSPI explained that it provided disaggregated data to assist school teams in their action planning. |
| Next Steps | In order to ensure that implementation of meaningful interventions aligned with all of the turnaround principles takes place in all priority schools for at least three years, ED will revisit, during Part B monitoring, the status of implementation in non-SIG priority schools and will review evidence and timelines related to this implementation. |

| Component 2.E | Work to close achievement gaps by publicly identifying Title I schools with the greatest achievement gaps, or in which subgroups are furthest behind, as focus schools and ensuring that each LEA implements interventions, which may include tutoring or public school choice, in each of these schools based on reviews of the specific academic needs of the school and its students beginning in the 2012-2013 school year. |
| --- | --- |
| Summary of Progress | OSPI indicated that focus schools developed initial action plans and submitted them to OSPI prior to August 31, 2012. These plans described actions to turn around low performance. Focus schools were implementing these plans at the time of the monitoring call. OSPI further noted that focus schools began completing needs assessments in September and October, 2012. Based on the needs assessment, focus schools may be adding additional interventions or modifying those currently being implemented. OSPI indicated that each focus school is provided with funding and at least 20 days of coaching to support the implementation of its action plan. Each school will receive an external needs assessment (in September and October, 2012). OSPI noted that the findings from the needs assessment will be used to develop their Student and School Success Action Plan. OSPI indicated that it provided disaggregated data to assist school teams in their action planning. OSPI noted that focus schools will craft their Student and School Success Action Plans using the online planning tool. |
| Next Steps | None. |

| Component 2.F | Provide incentives and supports to ensure continuous improvement in other Title I schools that, based on the SEA’s new AMOs and other measures, are not making progress in improving student achievement and narrowing achievement gaps beginning in the 2012-2013 school year. |
| --- | --- |
| Summary of Progress | Using its transitional system, OSPI has identified the next five percent of schools that would have been priority schools and the next 10 percent of schools that would have been focus schools as emerging schools, and targets incentives and supports to these other Title I schools. As OSPI transitions to identifying priority and focus schools based on its index, OSPI will use the index to identify emerging schools. OSPI indicated that it intends to update its emerging schools list each year. OSPI indicated that principals of emerging schools are invited to conversations being held for priority and focus schools when an LEA has priority and/or focus schools as well as emerging schools. OSPI noted that this is done in order for principals of emerging schools to understand the process of developing and implementing action plans based on the needs of the school. OSPI indicated it will host a webinar for all emerging school principals on Monday, October 8, 2012 and that the online planning tool will be available for use within a few days of the training. OSPI also indicated that it will launch an online platform to provide coaching in emerging schools beginning October 22, 2012. |
| Next Steps | None. |

| Component 2.G | Build SEA, LEA, and school capacity to improve student learning in all schools and, in particular, in low-performing schools and schools with the largest achievement gaps, including through: providing timely and comprehensive monitoring of, and technical assistance for, LEA implementation of interventions in priority and focus schools; holding LEAs accountable for improving school and student performance, particularly for turning around their priority schools; and ensure sufficient support for implementation of interventions in priority schools, focus schools, and other Title I schools identified under the SEA’s differentiated recognition, accountability, and support system (including through leveraging funds the LEA was previously required to reserve under ESEA section 1116(b)(10), SIG funds, and other Federal funds, as permitted along with State and local resources). |
| --- | --- |
| Summary of Progress | OSPI indicated it will use its process of consolidated reviews to hold LEAs accountable for improving school and student performance. OSPI noted it added two questions to its monitoring protocol to target schools that are labeled as focus, priority, or emerging. OSPI indicated it will conduct this monitoring between January and May 2013 and that it will follow its established follow-up system for consolidated reviews to ensure compliance at the LEA and school level. OSPI indicated that it has assigned state-level liaisons to each priority and focus school to support and monitor the school’s progress on its action plan and progress towards meeting its goals. As of October 5, 2012, all schools have had at least one onsite visit. These visits began at the beginning of the school year (2012-2013) and will continue throughout the academic year. OSPI indicated that four focus schools from two LEAs are not Title I, and that one LEA opted not to receive a school coach or to use any additional dollars. OSPI indicated that interventions will still be required in these schools and that they will be monitored closely. |
| Next Steps | None. |

### Fiscal

| Use of Funds | The SEA ensures that its LEAs use Title I funds consistent with the SEA’s approved ESEA flexibility request under Waivers 2, 3, 5, and 9 in the document titled ESEA Flexibility, and any unwaived Title I requirements. |
| --- | --- |
| Summary of Progress | OSPI indicated that it initially contacted superintendents by phone in the first days of July, 2012, and then provided guidance to its LEAs through webinars on August 17 and 22, 2012. OSPI further indicated that it frequently communicates with any LEAs that may have questions regarding funding flexibility. OSPI reported that its August 17, 2012 webinar covered the ways in which LEAs may use the 20 percent set-aside and other areas in which Title I funding is impacted by ESEA flexibility. |
| Next Steps | None. |

| Rank Order | The SEA ensures that LEAs with Title I eligible high schools with graduation rates below 60 percent that are identified as priority schools correctly implement the waiver that allows them to serve these schools out-of -rank order. |
| --- | --- |
| Summary of Progress | OSPI requested Waiver 13 and has identified Title I-eligible high schools with graduation rates below 60 percent as priority schools. Therefore, the SEA is taking advantage of the waiver and may have LEAs that implement the waiver by serving these schools out-of-rank order. OSPI provided guidance to its LEAs regarding this waiver through the webinars it conducted on August 17 and 22, 2012. OSPI indicated that it is ensuring that its LEAs implement this waiver correctly by including this element in its annual consolidated review monitoring protocol. |
| Next Steps | None. |